## Sprint3
Arabian Bank - Sprint3 - 16/Mar/2026 to 03/Apr/2026
S.No | Story (or) Activity | Description | Duration(In Days)
1 | Execute Baseline Test- Account Summary | Design the test to run with 5 users load with a duration of 10 min with a single login and single logout | 0.5
2 | Execute Baseline Test- DDRequest | Design the test to run with 5 users load with a duration of 10 min with a single login and single logout with a delay time of 5 mins. | 0.5
3 | Execute Baseline Test- FundTransfer | Design the test to run with 5 users load with a duration of 10 min but it should run once account summary scenario execution completes | 0.5
4 | Execute Baseline Test- Statements | Design the test to run with 5 users load with a duration of 15 min | 0.5
5 | Execute Baseline Test- Loan Apply | Design the test to run with 5 users load with 5 Iterations with a delay time of 10 mins. | 0.5
6 | Execute Baseline Test- Cards Apply | Design the test to run with 5 users load with 5 Iterations after a delay time of 10mins. | 0.5
S.No | Story (or) Activity | Description | Duration(In Days)
1 | Mixed Run1 | Run all 6 scripts together | 5
2 | Mixed Run2 | Run all 6 scripts together | 5
Execution Checklist
S.No | Activity
1 | Configure Grafana integration with JMeter
2 | Use Non-GUI mode of execution for each run
3 | Configure 1 Master and 5 Slaves to run the baseline tests
4 | Integrate JMeter scripts with GIT/Jenkins/CICD
5 | Configure and Run Infrastructure metrics on Windows/Linux boxes to monitor health of server system
6 | Configure and Run the Jconsole to monitor the health of JVM/GC