## Sprint1
Arabian Bank - Sprint1 - 8/Sep/2025 to 19/Sep/2025
S.No | Story (or) Activity | Duration(In Days)
1 | Walkthrough the PT Life cycle | 1
2 | Design the Performance Test Questionaire (or) Checklist | 2
3 | Walkthrough the Performance Test Questionaire | 1
4 | Walkthrough the AB Application and design traversal document | 1
5 | Perform PoC and Generate the PoC checklist | 2
6 | Design the Performance Test Plan | 2
7 | Review the test plan and Signoff | 1

## Sprint2
Arabian Bank - Sprint2 - 17/Feb/2025 to 13/Mar/2025
S.No | Individual Runs | Description | Duration(In Days)
1 | Develop the test script for scenario1 - Account Summary | Login account No and available balance amount should write into a file to use in the future purpose | 2
2 | Develop the test script for scenario2 - DDRequest | Wirte the commision amount into a file for the range of 100/1000/10000/100000 | 2
3 | Develop the test script for scenario3 - FundTrnsfer | Transfer the amount only if the account is having sufficient balance | 3
4 | Develop the test script for scenario4 - Statements | Generate the statements for the last six months | 2
5 | Develop the test script for scenario5 - Loan Apply | Apply for the loan but each account allows only one time apply | 3
6 | Develop the test script for scenario6 - Cards Apply | Apply for the card but each account allows only one time apply | 3
Scripting Checklist
S.No | Activity |  |  | 1 | IQ14285
1 | Transaction Names should be: <ApplicationName_ScenarioName_TNo_StepName |  |  | 2 | IQ14389
2 | In-corporate the proper thinktime on each webpage to simulate the realtime users |  |  | 3 | IQ14390
3 | Validate each webpage response before it runs |  |  | 4 | IQ14301
4 | All input values should be parameterized So no hard coded values to be presented in the script: format {P_} |  |  | 5 | IQ14302
5 | All server generated values should be correlated for smooth running of script: format {C_} |  |  | 6 | IQ14303
6 | Apply runtime error handling to handle the errors at runtime |  |  | 7 | IQ14306
7 | Use environment vairables to run the script in different environments |  |  | 8 | IQ14307
8 | Develop the script for test data preparation if any required |  |  | 9 | IQ14308
9 | All 360 degrees scripting challenges will be implemented
10 | Dry run the script with different input data parameters

## Sprint3
Arabian Bank - Sprint3 - 13/Oct/2025 to 24/Oct/2025
S.No | Story (or) Activity | Description | Duration(In Days)
1 | Execute Baseline Test- Account Summary | Design the test to run with 5 users load with a duration of 10 min with a single login and single logout | 1
2 | Execute Baseline Test- DDRequest | Design the test to run with 5 users load with a duration of 10 min with a single login and single logout after waiting for 5 min of test run started | 1
3 | Execute Baseline Test- FundTransfer | Design the test to run with 5 users load with a duration of 10 min but it should run once account summary scenario execution completes | 1
4 | Execute Baseline Test- Statements | Design the test to run with 5 users load with a duration of 15 min | 1
5 | Execute Baseline Test- Loan Apply | Design the test to run with 5 users load with 5 Iterations after waiting for 10 min of test runs started | 1
6 | Execute Baseline Test- Cards Apply | Design the test to run with 5 users load with 5 Iterations after waiting for 10 min of test runs started | 1
S.No | Story (or) Activity | Description | Duration(In Days)
1 | Mixed Run1 | All 360 degree realtime scenarios implemeted | 2
2 | Mixed Run2 | All 360 degree realtime scenarios implemeted | 2
Execution Checklist
S.No | Activity
1 | Configure Grafana integration with JMeter
2 | Use Non-GUI mode of execution for each run
3 | Configure 1 Master and 2 Slaves to run the baseline tests
4 | Integrate JMeter scripts with GIT/Jenkins/CICD
5 | Configure and Run Infrastructure metrics on Windows/Linux boxes to monitor health of server system
6 | Configure and Run the Jconsole to monitor the health of JVM/GC

## Sprint4
Arabian Bank - Sprint4 - 27/Oct/2025 to 07/Nov/2025
S.No | Story (or) Activity | Description | Duration(In Days)
1 | LoadTest Run1 (25% Load) | Design the test to run with 25% of peakload with a duration of 2 hours and Contineous monitoring the Servers environment | 1
2 | Load Test Run2 (50% Load) | Design the test to run with 50% of peakload with a duration of 2 hours and Contineous monitoring the Servers environment | 1
3 | LoadTest Run3(100% Full Load Test) | Design the test to run with 100% full load with a duration of 2 hours and Contineous monitoring the Servers environment | 1
4 | Endurance Test | Design the test to run with average amount of load for 12 hours continueous test and monitoring the overall servers health | 1
5 | Stress test | Design the test to run with 50% additional load for the peakload then apply stress test and monitoring the overall servers health | 1
S.No | Montoring Activities
1 | Contineous monitoring of Infrastructure resources of all Servers and Identify bottlenecks - Perfmon/Nmon
2 | Contineous monitoring of Java Application server parameters JVM/GC and Identify bottlenecks - Jconsole
3 | Contineous monitoring of Oracle Database server parameters and Identify bottlenecks - AWR Reports
4 | Contineous monitoring of end to end servers health - Dynatrace
5 | Collect and Analyze the thread dump and Heap dump
6 | Configure and Collect Java code level profiling - Jprofiler

## Sprint5
HealthCare (API)- Sprint5- 10/Nov/2025 to 21/Nov/2025
S.No | Story (or) Activity | API end points | Description | Duration(In Days)
1 | Microservice - InPatient | New Patient/Update Patient/Delete Patient |  | 2
2 | Microservice - OutPatient | New Patient/Update Patient/Delete Patient |  | 2
3 | Microservice - Appointments | Book Appointment/Update Appointment/Cancel Appointment |  | 2
4 | Microservice - Schedule | Find availability/Allocate schedule |  | 2
5 | Microservice - Doctors | Doctor types |  | 1
6 | Microservice - Medical Reports | All type of reports |  | 1
S.No | Monitoring Activities
1 | Contineous monitroing of Kubernetes/Container/Docker - Dynatrace/Cloudwatch in AWS cloud

## Sprint6
Arabian Bank - Sprint1 - 23/Nov/2025 to 28/Nov/2025
S.No | Story (or) Activity | Duration(In Days)
1 | Conparision Report | 2
2 | Summary Report | 3